## 00_Huong_dan_doc
Cách dùng file này
1. Sheet 01_Tong_quan — nhìn nhanh DONE / PARTIAL / STUB.
2. Sheet 02_Stack_ky_thuat — stack source để onboarding dev.
3. Sheet 03_Modules_trang_thai — inventory module chính (1 dòng = 1 module).
4. Sheet 04_Chi_tiet_tinh_nang — chi tiết tab/tính năng con.
5. Sheet 05_Backlog_chua_xong — ưu tiên phát triển tiếp.
6. Sheet 06_Router_API_map — map router FastAPI.
7. Sheet 07_Menu_dieu_huong — menu user/admin thực tế.
Quy ước màu Status: Xanh=DONE, Vàng=PARTIAL, Đỏ=PLANNED/STUB, Xanh dương=ADMIN_ONLY.
Phạm vi luật nội bộ: docs/luat.md — không đụng Content AI khi không được yêu cầu.
Codebase production: /var/www/seoauto_vn_usr4940/data/www/seoauto.vn
Xuất bởi Cursor agent dựa trên khảo sát source (không phải marketing copy).

## 01_Tong_quan
SEOAuto.vn — Inventory phát triển
Ngày xuất: 2026-07-29 14:55 (Asia/Ho_Chi_Minh)
Nguồn: khảo sát source production /var/www/seoauto_vn_usr4940/data/www/seoauto.vn
Chú thích trạng thái
DONE | Đã làm xong — dùng được production
PARTIAL | Có UI/API nhưng còn demo/mock/stub hoặc thiếu tích hợp
PLANNED/STUB | Chưa làm xong / chỉ stub / redirect / marketing
ADMIN_ONLY | Chỉ dành cho admin — đã có
Tóm tắt số lượng module
Trạng thái | Số module (ước lượng) | Ghi chú
DONE | 16 | Home, Auth, Dashboard/Report, Technical, Content AI core, KW Research, KW Clustering, SEO Score, Schema, Index Control, Settings core, Billing/SePay/Affiliate, Site Chatbot, Admin (hầu hết), Infra
PARTIAL | 8 | Rank Tracking, Keyword/SERP Intel, Google Map SEO, Chatbot CSKH, Social Auto, WP Plugin AI suggest, Admin Lead Scanner API, Publish Shopify/Haravan/Webcake
PLANNED/STUB | 4 | Keyword Hub UI thật, Zalo/Telegram CSKH, GBP Local Pack đối thủ live, WP plugin LLM suggest đầy đủ

## 02_Stack_ky_thuat
Lớp | Thành phần | Công nghệ / File chính | Ghi chú
Backend | Framework | FastAPI + Uvicorn (`main.py`) | Port production 8899
Backend | ORM / DB | SQLAlchemy 2.x → SQLite `app.db` hoặc PostgreSQL `DATABASE_URL` | Production có thể dùng PG
Backend | Auth | JWT (python-jose), bcrypt, OTP Gmail SMTP, Google OAuth login | `app/api/auth.py`, `otp_flow.py`
Backend | Template | Jinja2 SSR | `templates/*`
Backend | Crawl | Playwright, requests, BeautifulSoup4 | Technical SEO
Backend | Queue (tùy chọn) | Celery + Redis | Keyword jobs
Backend | Workers | `app/workers/*`, systemd timers | Social Auto scheduler, WP phase2
AI/LLM | Providers | OpenAI / Anthropic / OpenRouter catalog | `llm_content_writer.py`
AI/LLM | Images | OpenAI Image + Google CSE | Content AI images
AI/LLM | RAG KB | Embedding + knowledge docs | Settings AI Knowledge Base
Frontend | Kiểu | HTML/CSS/JS vanilla + TinyMCE (Content AI) | Không SPA React chính
Frontend | Theme | `digiseo-theme.css`, nav, dark mode, i18n vi/en | Accent #00e676
Tích hợp | Google | OAuth, GSC, GBP/My Business, Places, Blogger | Settings + Google Map + Social
Tích hợp | Publish | WordPress, Shopify, Haravan, Webcake | WP mạnh nhất
Tích hợp | Thanh toán | SePay webhook + VietQR / chuyển khoản | `/api/payments/sepay/webhook`
Tích hợp | SERP/Volume | SerpAPI, DataForSEO | Mock nếu thiếu key
Tích hợp | Index | IndexNow + checker providers | Index Control
Tích hợp | Social | Meta/Facebook Graph, Tumblr, Medium, Web2.0 | Social Auto
Ops | Nginx | FastPanel upstream → 127.0.0.1:8899 | proxy timeout Content AI 900s
Ops | Config | `env.local` | Secrets — không commit
Ops | Test | pytest | `tests/`
Ops | Docs nội bộ | `docs/digiseo_saas/*`, `docs/projects/*`, `docs/luat.md` | Một số doc May 2026 đã cũ hơn code Jul 2026

## 03_Modules_trang_thai
STT | Module (VI) | Module (EN) | URL / Path | Trạng thái | Tính năng chính đã có | Phần chưa xong / hạn chế | Template | JS chính | Router | Service chính | API ngoài | Ưu tiên phát triển tiếp
1 | Trang chủ | Landing | / | DONE | Landing marketing; auth modal; nav vào sản phẩm | — | home.html | digiseo-nav-auth.js | main.py / | — | — | Thấp
2 | Xác thực | Auth | /auth/* ; Google OAuth | DONE | Đăng ký/đăng nhập; OTP Gmail; JWT; Google login; admin skip OTP; credit APIs trên auth | UX onboarding có thể tinh chỉnh | partials/digiseo_auth_modal.html | digiseo-auth-*.js | app/api/auth.py | otp_flow, google_login, auth | SMTP, Google OAuth | Thấp
3 | Dashboard báo cáo | Dashboard / Report | /report ; /api/audit/* | DONE | Lịch sử audit; checklist; CSV/PDF/Sheets; action plan; GSC counts | GSC phụ thuộc OAuth + gói PRO | report.html | (inline/report JS) | report.py | report_builder | GSC API | Trung bình — polish SaaS dashboard
4 | Technical SEO | Technical Audit | /tool ; /analyze/* | DONE | Crawl site; checklist technical; nối report | Crawl nặng; chi phí ops | seo_tool.html | static/js/seo_tool/* | analyze.py | analyzer, seo_pipeline | Playwright | Thấp–Trung bình
5 | Content AI — Viết bài | Content AI Single | /content-ai (tab Viết bài SEO) | DONE | Suggest/stream LLM; outline; editor; ảnh; SEO score/autofix; internal links; publish checklist; projects; credit | Phụ thuộc LLM config; timeout nginx đã xử lý | content_ai/index.html | static/js/content_ai/* | pages.py /content-ai/* | llm_content_writer, content_ai_* | OpenAI/Anthropic | Cao — tối ưu tốc độ/chất lượng
6 | Content AI — Hàng loạt | Content AI Bulk | /content-ai (tab Viết hàng loạt) | DONE | Import; async jobs; worker; publish center; schedule; bulk images | Stub-content guards; placeholder images | content_ai partials | content_ai bulk JS | content_ai_bulk_* | content_ai_bulk_runner | LLM, WP | Cao
7 | Content AI — Auto Update | Content Auto Update | /content-ai (tab Auto Update) | DONE | Scan WP; AI SEO modal; preview; publish/draft; history/snapshot/restore | Cần WP connect | content_ai auto-update | content-ai-auto-update.js | content_auto_update.py | content auto update services | WP REST, LLM | Cao
8 | Nghiên cứu từ khóa | Keyword Research | /keywords/tools/research | DONE | Research sync/async; history; export Excel/Sheets | Volume phụ thuộc DataForSEO | keyword_research.html | keyword research JS | keywords.py | keyword_research_pipeline, dataforseo | DataForSEO | Trung bình
9 | Gom nhóm từ khóa | Keyword Clustering | /keywords/tools/clustering | DONE | Cluster sync/async; SERP-overlap/intent; export | SERP mock nếu thiếu SerpAPI | keyword_clustering.html | keyword-cluster-saas.js | keywords.py | keyword_cluster_pipeline | SerpAPI | Trung bình
10 | Theo dõi thứ hạng | Rank Tracking | /keywords/tools/rank-tracking | PARTIAL | UI + API + store | Cần SerpAPI; còn mock flags | rank_tracking.html | rank-tracking.js | rank_tracking.py | rank_tracking_store | SerpAPI | Cao
11 | Keyword Intelligence / Hub | KW Intel + Hub | /keyword-intelligence ; /keywords (redirect) | PARTIAL | SERP intel bundle; difficulty/opportunity APIs | Không SerpAPI → mock; Hub chỉ redirect, chưa UI hub thật | keyword_intelligence.html, keyword_hub.html | — | serp_intel.py, keyword_intelligence.py | serp_fetcher, serp_intel_bundle | SerpAPI | Cao
12 | SEO Score URL | SEO Score | /tool/seo-score | DONE | Chấm điểm URL; AI fix; apply WP | Apply WP cần credential publish | seo_url_score.html | seo score JS | seo_score.py | url_seo_scoreboard, seo_score_ai_fix | LLM, WP | Trung bình
13 | Schema JSON-LD | Schema Generator | /schema | DONE | Form types; analyze URL/HTML; preview/validate | — | schema_tool.html | schema-tool.js | schema.py | schema_* | — | Thấp
14 | Index Control | Index Control | /index-control | DONE | Submit Indexing; Check Index Free (+stream/export); IndexNow; quota gói; history | Một số path còn naming mock_type; docstring MVP | index_control.html | index-control.js | index_control.py | index_control_*, index_check_providers | IndexNow, Serp/site: | Trung bình
15 | Google Map SEO | Google Map / GBP | /google-map-seo (10 tabs) | PARTIAL | OAuth GBP; profile/review/posts/media AI; verification; lead scanner; Check Map score | Demo mode; reviews/reports/competitors demo; media API stub; Local Pack chưa live; Places config cho leads | google_map_seo.html | google-map-seo*.js | google_map_seo.py | google_map_gbp_*, lead_scanner | GBP APIs, Places, LLM | Cao
16 | Cài đặt | Settings | /settings | DONE | Account; API keys; AI provider; KB; Chatbot KB; Publishing (WP/Shopify/Haravan/Webcake); SEO Helper plugin; GSC; System | Copy cũ «khung»; Shopify/Haravan/Webcake mỏng hơn WP; GSC PRO | settings.html | settings-page.js, settings-chatbot-kb.js | settings_api.py | wp_connect, shopify_connect, ai_knowledge_store | Google, platform REST | Trung bình
17 | Tài khoản & Thanh toán | Account Billing | /account-billing ; /pricing | DONE | Gói; hóa đơn; VietQR/CK; SePay webhook; credit packages; VAT; overview | Cần SEPAY_* trên prod | account_billing.html, pricing.html | account-billing.js, sepay-payment-flow.js | saas.py, payments.py | sepay_webhook_service | SePay | Trung bình — vận hành
18 | Affiliate | Affiliate | /account-billing?tab=affiliate ; /affiliate/* ; /admin/affiliate | DONE | Chương trình giới thiệu user + admin | — | account_billing + admin_affiliate | affiliate JS | affiliate.py, admin_affiliate.py | affiliate services | — | Thấp
19 | Chatbot site FAQ | Site Chatbot | /chatbot/* widget | DONE | Floating assistant; FAQ KB; workflows; credit gate | Cần LLM entitlement | partials/digiseo_chatbot.html | digiseo-chatbot.js | chatbot.py | chatbot_* | LLM | Thấp
20 | Chatbot CSKH | CSKH Chatbot | /chatbot-cskh | PARTIAL | Bot CRUD; crawl KB; widget web; inbox; Facebook Messenger beta | Không có Zalo/Telegram router; Free = demo; FB beta 24h | chatbot_cskh.html | chatbot-cskh.js | chatbot_cskh*.py | chatbot_cskh_* | Meta Messenger, LLM | Cao
21 | Social Auto | Social Auto | /social-auto | PARTIAL | Campaigns; FB OAuth publish/schedule; Web2.0 (Blogger/Tumblr/Medium/WP/Sites); safety; scheduler | Mock modes; production guard chặn mock publish; docstring cũ «demo» | social_auto.html | social-auto.js | social_auto.py, social_auto_web20.py | social_auto_*, web20_providers | Meta, Blogger, Tumblr | Cao
22 | WordPress Plugin API | SEO Helper Plugin | /api/wordpress-plugin/* | PARTIAL | Pairing; connections; jobs; updates; publish-guard; entitlements | AI suggestions = heuristic stub, chưa LLM đầy đủ | settings SEO Helper UI | — | wordpress_plugin.py | wordpress_plugin_*, phase2_worker | WP plugin ↔ SaaS | Cao
23 | Admin Users | Admin Users | /admin | ADMIN_ONLY | Quản lý user; API access; pool; audit | — | admin.html | admin-*.js | admin.py | admin services | — | Thấp
24 | Admin Pricing/Quotas/Credits | Admin SaaS config | /admin/pricing, credit-costs, plan-quotas | ADMIN_ONLY | Plans; credit costs; quotas | — | admin_pricing, admin_credit_costs, admin_plan_quotas | admin JS | saas_admin.py | plan/credit services | — | Thấp
25 | Admin Billing / Backup / Integrations / Economics | Admin Ops | /admin/billing, backup, integrations, saas-economics | ADMIN_ONLY | Đơn hàng; backup; integrations; economics dashboard | — | admin_*.html | admin JS | admin_billing, backup, integrations, saas_economics | tương ứng | — | Thấp
26 | Admin Lead Scanner | Admin Lead Scanner | /admin/api/lead-scanner/* | PARTIAL | Status/usage stats | UX scanner nằm ở Google Map; admin chỉ status | — | — | admin_lead_scanner.py | lead scanner | Places | Thấp
27 | Hạ tầng | Infrastructure | uvicorn :8899 + nginx | DONE | FastAPI; DB; JWT; workers; health; env.local | Monitoring/support ticket theo roadmap SaaS còn thiếu | — | — | main.py | db, workers | — | Trung bình — monitoring

## 04_Chi_tiet_tinh_nang
Module | Nhóm / Tab | Tính năng chi tiết | Trạng thái | Ghi chú kỹ thuật
Content AI | Viết bài SEO | Gợi ý title/meta/slug/tags/keywords | DONE | /content-ai/suggest
Content AI | Viết bài SEO | Gợi ý outline + content LLM (sync/stream) | DONE | Timeout nginx 900s cho suggest
Content AI | Viết bài SEO | Editor + SEO score / autofix | DONE
Content AI | Viết bài SEO | Ảnh AI / Google Images / thumbnail | DONE
Content AI | Viết bài SEO | Internal links + publish checklist | DONE
Content AI | Viết bài SEO | Projects CRUD / export | DONE
Content AI | Viết hàng loạt | Import file + async jobs + worker | DONE
Content AI | Viết hàng loạt | Publish center + schedule board | DONE
Content AI | Viết hàng loạt | Bulk images | DONE | content_ai_bulk_images
Content AI | Auto Update | Scan bài WP + lọc điểm SEO | DONE
Content AI | Auto Update | AI đề xuất / rewrite / insert | DONE
Content AI | Auto Update | Preview + publish/draft + lịch sử/restore | DONE
Google Map | Tổng quan | Chọn địa điểm + stats + kết nối GBP | PARTIAL | Demo mode nếu chưa OAuth
Google Map | Check Map | Chấm điểm hồ sơ Map (client engine) | DONE | google-map-seo-check.js — đã fix SyntaxError
Google Map | Tối ưu hồ sơ | AI generate draft + apply GBP | PARTIAL | Cần OAuth + quyền API
Google Map | Review | List review + AI reply + post reply | PARTIAL | Fallback demo data
Google Map | Bài đăng | Draft / schedule / publish Local Posts | PARTIAL | GBP Posts API
Google Map | Ảnh & Media | Upload / caption AI / publish | PARTIAL | media API v4 stub
Google Map | Xác minh Map | Verification kit + assets | PARTIAL
Google Map | Đối thủ | Phân tích đối thủ local | PARTIAL | Local Pack/Places chưa đủ
Google Map | Báo cáo | Snapshot + export CSV/PDF + branding | PARTIAL | Demo khi thiếu data
Google Map | Lead Scanner | Quote / scan / history / export / lấy SĐT | PARTIAL | Cần GOOGLE_PLACES_API_KEY + credit
Index Control | Submit Indexing | Project + submit URL + quota gói | DONE | IndexNow
Index Control | Check Index Free | Check + stream + export | DONE | Providers đa dạng
Index Control | Tổng quan / Kết quả | History overview | DONE
Settings | Xuất bản | WordPress connect + publish | DONE | Mạnh nhất
Settings | Xuất bản | Shopify connect | PARTIAL | Mỏng hơn WP
Settings | Xuất bản | Haravan connect | PARTIAL | Mỏng hơn WP
Settings | Xuất bản | Webcake connect | PARTIAL | Mỏng hơn WP
Settings | SEO Helper | Download plugin + pairing | DONE | ZIP static download
Settings | GSC | OAuth Search Console | DONE | PRO gated
Settings | Knowledge Base | RAG Content AI + Chatbot KB | DONE
Social Auto | Facebook | OAuth + publish/schedule | PARTIAL | Mock mode có thể bật
Social Auto | Web 2.0 | Blogger/Tumblr/Medium/WP/Sites | PARTIAL | WEB20_BLOGGER_MOCK
Social Auto | Scheduler | Timer systemd + API | DONE | deploy/social-auto-scheduler
Chatbot CSKH | Website widget | Embed + inbox | DONE
Chatbot CSKH | Facebook Messenger | Webhook beta | PARTIAL | Cửa sổ 24h
Chatbot CSKH | Zalo | Kênh Zalo | PLANNED/STUB | Chưa có router
Chatbot CSKH | Telegram | Kênh Telegram | PLANNED/STUB | Chưa có router
WP Plugin | Pairing / updates | Pairing codes, download updates | DONE
WP Plugin | AI SEO suggestions | Enqueue/poll suggestions | PLANNED/STUB | _run_ai_suggest_async_stub
Billing | Gói SaaS | Plans + entitlement + trial | DONE
Billing | Thanh toán | Tạo đơn + VietQR + SePay webhook | DONE | Cần cấu hình SEPAY
Billing | Credit | Ledger + quote + charge theo feature | DONE
Billing | Affiliate | Hoa hồng user + admin | DONE
Keyword | Research | Nghiên cứu + volume + export | DONE | DataForSEO
Keyword | Clustering | Gom nhóm + jobs | DONE
Keyword | Rank Tracking | Theo dõi hạng theo kỳ | PARTIAL | Mock nếu thiếu SerpAPI
Keyword | Intelligence | Difficulty/opportunity SERP bundle | PARTIAL | Mock SERP
Keyword | Hub | Trang hub đa công cụ | PLANNED/STUB | Redirect → research

## 05_Backlog_chua_xong
Ưu tiên | Module | Hạng mục chưa xong | Loại | Gợi ý hướng làm | File liên quan
1 | Rank Tracking | Bỏ mock — chạy live SerpAPI ổn định + cron refresh | PARTIAL→DONE | Bật SERPAPI_KEY; worker định kỳ; UI lịch sử hạng | rank_tracking.py, rank_tracking_store.py
1 | Keyword / SERP Intel | Hub UI thật + SERP live (không mock mặc định) | PARTIAL | Trang hub đa tab; fail-soft khi thiếu key | serp_fetcher.py, keyword_hub.html
1 | Google Map | Tắt demo khi đã OAuth; reviews/reports/competitors live | PARTIAL | Bỏ fallback demo; wire Places Local Pack | google_map_gbp_*_service.py
1 | Google Map | Media API v4 stub → upload/publish thật | STUB | Hoàn thiện google_map_gbp_media_api.py | google_map_gbp_media_api.py
1 | Social Auto | Tắt mock production; publish FB/Web2.0 tin cậy | PARTIAL | Env mock=0; monitoring lỗi Graph API | social_auto_*, web20_providers
1 | Chatbot CSKH | Zalo OA + Telegram bot | PLANNED | Router + webhook riêng; entitlement gói | chưa có router
1 | WP Plugin | AI suggestions LLM thật thay stub | STUB | Thay _run_ai_suggest_async_stub bằng LLM off-band | wordpress_plugin_phase2_service.py
2 | Settings Publish | Shopify / Haravan / Webcake parity với WP | PARTIAL | Test publish E2E từng platform | shopify_connect.py, webcake_connect.py
2 | Content AI | Tối ưu latency content suggest (<60–90s) | DONE core | Cache website context; stream UX; worker async | llm_content_writer.py
2 | Google Map | Lead Scanner Places + credit UX polish | PARTIAL | Admin config Places; báo cáo usage | google_map_lead_scanner_service.py
2 | Index Control | Chuẩn hóa provider naming; bỏ nhãn MVP | DONE core | Cleanup mock_type labels | index_control_*
2 | Infra SaaS | Monitoring/logging/alerting production | PLANNED | Theo docs/digiseo_saas/15-monitoring-logging.md | docs + ops
2 | Infra SaaS | Support ticket / feedback | PLANNED | docs/digiseo_saas/16-support-feedback.md | chưa module
3 | Dashboard | Onboarding SaaS chuyên nghiệp | PARTIAL | docs/08-user-dashboard-onboarding.md | report.html
3 | Docs | Cập nhật 03-module-status.md cho khớp code Jul 2026 | DOCS | Billing/Map/Social/CSKH đã có nhiều hơn doc May | docs/digiseo_saas/03-module-status.md
3 | E2E | Bộ E2E test theo roadmap | PLANNED | docs/19-e2e-testing.md | tests/

## 06_Router_API_map
Router file | Prefix / Mount | Phạm vi chức năng
app/api/auth.py | /auth/* | Login/register/OTP/Google/credits
app/routers/pages.py | HTML pages + /content-ai/* | SSR pages + Content AI APIs lớn
app/routers/analyze.py | /analyze/* | Technical analyze
app/routers/report.py | /report, /api/audit/* | Dashboard report
app/routers/seo_score.py | /api/seo-score/* | SEO Score AI fix
app/routers/schema.py | /schema, /api/schema* | Schema generator
app/routers/keywords.py | /keywords/* | Research + clustering
app/routers/rank_tracking.py | /api/rank-tracking/* | Rank tracking
app/routers/serp_intel.py | /api/serp/* | SERP intelligence
app/routers/keyword_intelligence.py | /api/keyword-intelligence | KW intel
app/routers/index_control.py | /api/index-control/* | Index submit/check
app/routers/google_map_seo.py | /api/google-map-seo/* | GBP + Lead Scanner
app/routers/settings_api.py | /api/settings/* | Settings
app/routers/integrations_google.py | Google integrations | GSC OAuth
app/routers/content_auto_update.py | /content-ai/auto-update/* | Auto Update
app/routers/content_ai_bulk_publish.py | bulk publish | Bulk publish
app/routers/content_ai_bulk_images.py | bulk images | Bulk images
app/routers/internal_links.py | /internal-links/* | Internal links
app/routers/wp_bulk_update.py | WP bulk | WP bulk update
app/routers/wordpress_plugin.py | /api/wordpress-plugin/* | SEO Helper plugin
app/routers/saas.py | /api/saas/* | Plans/subscriptions/orders
app/routers/payments.py | /api/payments/* | SePay webhook
app/routers/affiliate.py | /affiliate/* | Affiliate user
app/routers/chatbot.py | /chatbot, /api/chatbot | Site chatbot
app/routers/chatbot_cskh*.py | /api/chatbot-cskh, /api/chatbot/* | CSKH bots/kb/inbox/FB
app/routers/social_auto.py | /api/social/* | Social campaigns
app/routers/social_auto_web20.py | /api/social/web20/* | Web 2.0
app/routers/admin*.py + saas_admin.py | /admin, /admin/api/* | Admin panels
app/routers/trial_api.py | /api trial | Trial
app/routers/credits_preview.py | /api credits preview | Credit quote UI
app/routers/user_files.py | user files | Upload files
app/routers/seo_public.py | public SEO | Public endpoints

## 07_Menu_dieu_huong
Vị trí | Nhãn | URL | Ghi chú
Top nav user | Dashboard | /report | digiseo_main_nav.html
Top nav user | Technical | /tool
Top nav user | Content AI | /content-ai | 3 tabs nội bộ
Top nav user | Keyword | /keywords/tools/research | Sub: research/clustering/rank-tracking
Top nav user | SEO Score | /tool/seo-score
Top nav user | Schema | /schema
Top nav user | Index Control | /index-control
Top nav user | Google Map | /google-map-seo | 10 sidebar tabs
Top nav user | Cài đặt | /settings
Top nav user | Tài khoản & Thanh toán | /account-billing
Keyword subnav | Nghiên cứu từ khóa | /keywords/tools/research
Keyword subnav | Gom nhóm từ khóa | /keywords/tools/clustering
Keyword subnav | Theo dõi thứ hạng | /keywords/tools/rank-tracking
Extra pages | Social Auto | /social-auto | Nav phụ digiseo-social-auto-nav.js
Extra pages | Chatbot CSKH | /chatbot-cskh | Nav phụ digiseo-chatbot-cskh-nav.js
Extra pages | Pricing | /pricing | Public
Extra pages | Keyword Intelligence | /keyword-intelligence | Ít nổi trên main nav
Admin shell | Quản lý User | /admin
Admin shell | Affiliate | /admin/affiliate
Admin shell | Pricing / Plans | /admin/pricing
Admin shell | Credit costs | /admin/credit-costs
Admin shell | Plan quotas | /admin/plan-quotas
Admin shell | Billing | /admin/billing
Admin shell | Backup | /admin/backup
Admin shell | Integrations | /admin/integrations
Admin shell | SaaS economics | /admin/saas-economics