## Feature Checklist
Module | Feature | Status | Org isolation | Auth/RBAC | Credit/SaaS | Queue/Worker | File/Evidence | Notes | Test result
Auth | Password + OTP register/login | ✅ Hoàn thành | ✅ | ✅ | N/A | N/A | app/api/auth.py, app/services/auth.py | JWT cookie + Bearer | Tests: test_auth_session_google.py (suite related)
Auth | Google OAuth login | ✅ Hoàn thành | ✅ | ✅ | N/A | N/A | app/services/google_login.py | State JWT bound | OK in code
Auth | RBAC roles (admin/user/editor/viewer) | ⚠️ Chưa hoàn thiện | ⚠️ | ⚠️ | N/A | N/A | app/services/rbac.py | Không có permission matrix chi tiết; org member role schema-only | Manual
Auth | CSRF cookie protection | ✅ Hoàn thành | N/A | ✅ | N/A | N/A | app/services/csrf_middleware.py | Exempt SePay/WP/public CSKH | 3 CSRF tests failed in local run (env/schema side-effect)
Multi-tenant | Personal org (org_id=user_id) | ⚠️ Chưa hoàn thiện | ⚠️ | ✅ | ⚠️ | N/A | app/services/tenant_org.py, models/organization.py | Chưa có shared-org UI; resolver không check membership | Code review
Multi-tenant | Content AI projects PG org isolation | ✅ Hoàn thành | ✅ | ✅ | ✅ | ✅ | content_ai_projects_pg.py | Có filter org+user | test_content_ai_projects_org_isolation PASSED
Multi-tenant | Publishing sites / WP pairing org | ✅ Hoàn thành | ✅ | ✅ | ⚠️ | ✅ | wordpress_pairing_service.py (strict) | WP path reject foreign org | test_publishing_sites_org_isolation PASSED
Multi-tenant | tenant_org.resolve_organization_id | ❌ Lỗi/chưa hoạt động | ❌ | ⚠️ | N/A | N/A | app/services/tenant_org.py:14-18 | Trust client org_id không membership check | Code verified
Billing | Trial 3 ngày | ✅ Hoàn thành | ⚠️ user-scoped | ✅ | ✅ | N/A | saas_trial_service.py | Caps + blocked features | test_saas_trial_3d present
Billing | Plans / subscriptions / checkout | ✅ Hoàn thành | ⚠️ user-scoped | ✅ | ✅ | N/A | payment_order_service.py, payment_activation_service.py | Bank transfer SePay | Code + tests
Billing | Credit ledger + reserve/commit/release | ✅ Hoàn thành | ⚠️ audit org only | ✅ | ✅ | ✅ | credits.py, credit_reservation.py | FOR UPDATE; FIFO buckets | test_credit_ledger_v2 / celery retry PASSED
Billing | Central saas_action_gate adoption | ⚠️ Chưa hoàn thiện | ⚠️ | ✅ | ⚠️ | N/A | saas_gate.py | Nhiều endpoint vẫn bypass / module gate riêng | test_saas_central_gate present
Billing | SePay webhook idempotency | ✅ Hoàn thành | N/A | ⚠️ | ✅ | N/A | sepay_webhook_service.py | Durable event store + unique tx | test_sepay_webhook* PASSED
Billing | SePay webhook auth (default) | ❌ Lỗi/chưa hoạt động | N/A | ❌ | N/A | N/A | payment_config.py sepay_webhook_require_auth→False | Unsigned payload accepted by default; prod env thiếu SEPAY_WEBHOOK_REQUIRE_AUTH | Code + env check
Billing | Payment reconciliation | ✅ Hoàn thành | N/A | ✅ admin | ✅ | scripts | payment_reconciliation_service.py | Repair failed activations | Script exists
Queue | Celery + Redis crawl/keyword/WP | ✅ Hoàn thành | ⚠️ | ✅ | ✅ keyword | ✅ | queue/celery_app.py, workers/* | acks_late, prefetch=1 | Code
Queue | Async task owner registry | ❌ Lỗi/chưa hoạt động | ❌ | ⚠️ | N/A | ❌ | async_task_registry.py | In-memory only → multi-worker broken/IDOR risk | Code verified
Queue | DistributedCrawlJob tenancy | ❌ Lỗi/chưa hoạt động | ❌ | ⚠️ | N/A | ⚠️ | models/crawl_job.py | Không có user_id/organization_id | Code verified
Queue | Content AI bulk worker (SKIP LOCKED) | ✅ Hoàn thành | ⚠️ | ✅ | ✅ | ⚠️ scale | content_ai_bulk_runner.py / worker_loop | In-process daemon; FOR UPDATE SKIP LOCKED tốt | Code
Content AI | Write / outline / brief / projects | ✅ Hoàn thành | ⚠️ dual JSON/PG | ✅ | ✅ | ✅ | routers/pages.py, content_ai_* | Mature module | Many unit tests
Content AI | Images / studio / insert | ✅ Hoàn thành | ⚠️ | ✅ | ✅ | ⚠️ | content_ai_image_* | Charge on success | image tests present
Content AI | Duplicate detection | ✅ Hoàn thành | ⚠️ | ✅ | ✅ | N/A | content_ai_duplicate_detection.py |  | test_content_ai_duplicate_detection
Content AI | Auto update (CAU) | ✅ Hoàn thành | ⚠️ | ✅ | ✅ | N/A | content_auto_update.py | Modal + patches + credits | CAU tests
Content AI | Bulk publish / schedule | ⚠️ Chưa hoàn thiện | ⚠️ schedule user-only | ✅ | ✅ | ✅ | content_ai_publish_schedule.py | Schedule thiếu organization_id; DUAL_READ=1 prod | Code + env TENANT_CONTENT_AI_DUAL_READ=1
Keyword | Keyword Research | ✅ Hoàn thành | ❌ user-only | ✅ | ✅ | ⚠️ async optional | keywords.py, keyword_tasks.py | Celery gated by env | Code
Keyword | Keyword Clustering | ✅ Hoàn thành | ❌ | ✅ | ✅ | ✅ | cluster_* + keyword_cluster_worker |  | Code
Keyword | Suggestion tab UI | ❌ Lỗi/chưa hoạt động | N/A | N/A | N/A | N/A | templates/keyword_research.html ~stub | Explicit stub | UI review
Keyword | Keyword Intelligence API | ⚠️ Chưa hoàn thiện | ❌ | ❌ no auth | ❌ | N/A | keyword_intelligence.py | Public unauthenticated API | Code verified
Technical SEO | Analyze / crawl / report dashboard | ✅ Hoàn thành | ⚠️ user projects | ✅ trial | ✅ | ✅ crawl worker | analyze.py, seo_tool.html | Timeout releases reservation | Code
SEO Score | URL SEO scoreboard | ✅ Hoàn thành | ❌ | ✅ trial | ✅ | N/A | analyze url-seo-scoreboard |  | Code
SEO Score | AI Fix billing | ❌ Lỗi/chưa hoạt động | ❌ | ✅ | ❌ default off | N/A | seo_score_ai_fix.py SEO_SCORE_AI_FIX_BILLING_ENABLED | LLM free by default while registry has cost | Code verified
Index Control | Check / submit / IndexNow / history | ✅ Hoàn thành | ❌ user-only | ✅ | ⚠️ quota only | ThreadPool | index_control.py | Không trừ credit wallet; dùng plan quota | Code
Google Map SEO | GBP OAuth / profile / posts / reviews / media | ⚠️ Chưa hoàn thiện | ❌ user-only | ✅ | ❌ AI unmetered | N/A | google_map_seo.py + gbp_*_ai.py | AI generate không consume_credits | Code verified
Google Map SEO | Plan location capacity | ✅ Hoàn thành | ❌ | ✅ | ⚠️ entitlement | N/A | google_map_gbp_* capacity asserts |  | Code
Lead Scanner | Scan / detail / export + credits | ✅ Hoàn thành | ❌ user-only | ✅ | ✅ | N/A | google_map_lead_scanner_service.py | UI nằm trong Google Map, không standalone | Code
WordPress | Plugin pairing / publish / phase2 | ✅ Hoàn thành | ✅ strict org | ✅ | ⚠️ entitlement | ✅ Celery | wordpress_plugin.py, workers |  | Code
WordPress | WP bulk update | ⚠️ Chưa hoàn thiện | ❌ | ✅ | ❌ no credit gate | scripts/wp_bulk_worker.py | wp_bulk_update.py | Auth only | Code
Chatbot CSKH | Bots / KB / inbox / Facebook / widget | ✅ Hoàn thành | ❌ user/bot | ✅ | ✅ reply quota+overage | N/A | chatbot_cskh_* | Dual mount /api/chatbot vs /api/chatbot-cskh | Code
Chatbot CSKH | Public widget API | ✅ Hoàn thành | bot_id | public+rate limit | ✅ overage path | N/A | chatbot_cskh_public.py | CORS * + validate_bot_id | Code
Rank Tracking | Projects / keywords / check-now | ❌ Lỗi/chưa hoạt động | ❌ | ✅ | ❌ unmetered DataForSEO | ❌ JSON no lock | rank_tracking.py + rank_tracking_store.py | JSON file race + free SERP | test_rank_tracking_* mostly unit OK; billing missing
Schema Tool | Preview / validate / generate | ❌ Lỗi/chưa hoạt động | ❌ | ❌ no auth | ❌ | N/A | schema.py | schema-generator có thể gọi fetch_serp không auth/credit | Code verified
Social Auto | Social + Web2.0 publishing | ⚠️ Chưa hoàn thiện | ❌ | ✅ | ⚠️ quota | N/A | social_auto*.py | Ngoài scope ưu tiên nhưng ship kèm | Code
Affiliate | Affiliate + SePay paid hook | ✅ Hoàn thành | N/A | ✅ | N/A | N/A | affiliate_*, affiliate_payment_hooks.py | Errors swallowed after pay | Tests present
Admin | Admin billing / plans / integrations / backup | ✅ Hoàn thành | admin | ✅ | N/A | N/A | admin_*.py |  | Tests present
SERP Intel | POST /api/serp-intel | ⚠️ Chưa hoàn thiện | ❌ | ❌ | ❌ | N/A | serp_intel.py | Unauthenticated compute endpoint | Code

## Code Issues
ID | Severity | Category | Title | File/Code | Root cause | Fix | How to test | Status | Notes
ISSUE-001 | P0 | Security/Billing | SePay webhook auth default OFF — unsigned payload accepted | app/services/payment_config.py (sepay_webhook_require_auth), app/routers/payments.py | SEPAY_WEBHOOK_REQUIRE_AUTH mặc định False; chỉ cần payload có tx_id+account+amount là pass. Prod env không set flag này. | Default require_auth=True khi is_production(); bắt buộc SEPAY_WEBHOOK_REQUIRE_AUTH=1 + API key/HMAC trên SePay dashboard. | POST /api/payments/sepay/webhook forged body matching bank account + pending order code → 401; với Apikey đúng → 200 1 lần activate. | Open | Pre-release blocker
ISSUE-002 | P0 | Billing/Cost | Rank Tracking check-now gọi DataForSEO không trừ credit / không SaaS gate | app/routers/rank_tracking.py, app/services/rank_tracking_service.py | Endpoint chỉ Depends(get_current_user); không enforce_saas_access / saas_action_gate / consume_credits. | Thêm credit_cost_registry rank_tracking/* + saas_action_gate trước check; fail 402 khi thiếu credit. | User hết credit gọi check-now → 402; user đủ credit → balance giảm đúng 1 lần; idempotent nếu retry. | Open | Pre-release blocker
ISSUE-003 | P0 | Data integrity | Rank Tracking JSON store race — mất dữ liệu khi concurrent write | app/services/rank_tracking_store.py (_read_list/_write_list) | Read-modify-write toàn file không file lock / không PG; multi-worker uvicorn sẽ ghi đè. | Migrate PG (user_id, org_id indexes) hoặc interim fcntl/portalocker + atomic replace; thêm unique constraints. | 2 client song song create project → cả 2 record còn; không mất row. | Open | Pre-release blocker
ISSUE-004 | P0 | Billing/Cost | Google Map GBP AI (profile/post/review/media) unmetered LLM | google_map_gbp_*_ai.py, google_map_gbp_*_service.py, routers/google_map_seo.py | AI generate gọi OpenAI/OpenRouter; router auth=1 nhưng credit=0; không consume_credits. | Wire saas_action_gate + registry module google_map; reserve trước LLM, commit on success, release on fail. | Mỗi AI action ghi ledger; balance giảm; fail LLM không trừ (release). | Open | Pre-release blocker
ISSUE-005 | P0 | Billing/Cost | SEO Score AI Fix billing flag default OFF | app/services/seo_score_ai_fix.py, credit_cost_registry.py | finalize_seo_score_ai_fix_credit no-op trừ khi SEO_SCORE_AI_FIX_BILLING_ENABLED=1. | Bật flag prod hoặc ẩn AI Fix; align UI copy với billing. | AI fix success → debit; flag off → endpoint 403 hoặc không expose. | Open | Pre-release blocker
ISSUE-006 | P0 | Security | Schema generator + Keyword Intelligence + SERP Intel public không auth | app/routers/schema.py, keyword_intelligence.py, serp_intel.py | Không Depends(get_current_user); schema-generator có thể fetch_serp (chi phí API). | Bắt buộc auth + saas_action_gate; rate-limit guest nếu cố tình public; tắt fetch_serp với anonymous. | Unauth POST /schema-generator → 401; auth + hết credit → 402. | Open | Pre-release blocker
ISSUE-007 | P0 | Tenant | tenant_org.resolve_organization_id tin client org_id | app/services/tenant_org.py:14-18; callers content_ai_projects_pg, publishing_sites_pg, job_store, user_api_keys_db | Trả về bất kỳ organization_id>0 không gọi user_belongs_to_organization. WP pairing thì đúng (strict). | Luôn membership-check hoặc force personal org cho đến khi multi-org ship; align wordpress_pairing_service. | User A create với organization_id=B → 403; list không thấy data B. | Open | Blocker nếu ship multi-org; Medium nếu personal-only nhưng phải fix trước shared org
ISSUE-008 | P1 | Queue/Security | async_task_registry in-memory — poll IDOR / 404 multi-worker | app/services/async_task_registry.py, keywords.py | Dict process-local; restart/multi-uvicorn mất ownership map. | Persist Redis/DB TTL task_id→user_id lúc enqueue. | Enqueue worker A, poll worker B vẫn assert owner đúng. | Open
ISSUE-009 | P1 | Tenant | DistributedCrawlJob thiếu user_id/organization_id | app/models/crawl_job.py, queue/crawl_queue.py, workers/crawl_worker.py | Job chỉ có project_id optional; không bind tenant trên job row. | Add columns + filter enqueue/read APIs. | User A không đọc được job_id của B. | Open
ISSUE-010 | P1 | Billing race | reserve_credits không catch IntegrityError duplicate idempotency | app/services/credits.py reserve_credits (~838+) | Check-then-insert; unique key có nhưng race → 500 thay vì return existing. | except IntegrityError: reload by key, return same shape. | Parallel same-key reserve → 1 debit, cả 2 caller nhận cùng reservation_id. | Open
ISSUE-011 | P1 | Billing ops | SePay process exception vẫn HTTP 200 success | app/routers/payments.py except block ~108-118 | Ẩn lỗi hạ tầng; SePay không retry; phụ thuộc reconciliation. | 5xx cho infra fail sau khi event stored failed; alert backlog; giữ 200 cho business skip. | Force activate raise → event failed + reconcile repair. | Open
ISSUE-012 | P1 | Security | JWT expire mặc định 720 giờ (30 ngày) | app/core/security.py | JWT_EXPIRE_HOURS default 720. | Giảm prod 24–72h + refresh token hoặc rotate. | Token hết hạn bị reject; cookie max-age khớp. | Open
ISSUE-013 | P1 | Tenant/Data | Content AI dual-read JSON+PG còn bật (TENANT_CONTENT_AI_DUAL_READ=1) | tenant_content_ai_flags.py, env.local | Fallback JSON có thể mask PG miss / stale tenant data. | Tắt dual-read sau verify cutover; monitor miss rate. | PG miss không trả JSON của user khác. | Open | Prod flag confirmed =1
ISSUE-014 | P1 | Tenant | Publish schedule / Index Control / GBP / Rank / CSKH thiếu organization_id | content_ai_publish_schedule.py, models/index_control.py, google_map_gbp*, rank_tracking_store, chatbot_cskh* | Isolation chỉ user_id — chưa sẵn sàng team workspace. | Migrate org column + resolve membership; tạm document personal-only. | Cross-user IDOR tests xanh; shared-org deferred. | Open
ISSUE-015 | P1 | Billing | WP bulk update không credit/SaaS gate | app/routers/wp_bulk_update.py | Chỉ get_current_user; không enforce_saas_access. | Thêm entitlement wp_publish + optional credit/quota. | Plan không có WP → 403; có plan → job enqueue. | Open
ISSUE-016 | P1 | Product | Keyword Research suggestion tab là stub | templates/keyword_research.html | UI tab stub gây hiểu nhầm feature live. | Gỡ tab hoặc nối API thật. | UI không còn stub label. | Open
ISSUE-017 | P1 | Scale | Content AI bulk worker in-process only | main.py lifespan, content_ai_bulk_worker_loop | Horizontal scale cần worker riêng; nhiều process có thể duplicate nếu misconfig. | Deploy dedicated worker; document CONTENT_AI_BULK_WORKER_AUTO; đảm bảo claim SKIP LOCKED single owner. | 2 workers claim khác job; không double-process cùng job_id. | Open
ISSUE-018 | P1 | API hygiene | Chatbot CSKH dual API prefixes | main.py mounts /api/chatbot và /api/chatbot-cskh | Duplicate endpoints → client lệch / docs lệch. | Canonical 1 prefix; redirect/deprecate cái còn lại. | Client chỉ gọi 1 base path. | Open
ISSUE-019 | P1 | Test/Deploy | Schema credit_reservations có thể thiếu trên DB → runtime hard fail | app/migrations/ensure_credit_saas_gate.py | Local/test run: RuntimeError table:credit_reservations missing; CSRF/isolation tests fail theo side-effect. | Chạy migration trước release; CI assert schema; startup check rõ ràng. | pytest suite + app boot không raise missing table. | Open | Observed in pytest: 5 failed related
ISSUE-020 | P2 | Billing consistency | Index Control chỉ quota, không credit registry | index_control.py, credit_cost_registry.py | Chi phí Google/API không đi wallet thống nhất. | Quyết định policy: quota-only có chủ đích thì document; hoặc add costs. | Quota exceed trả mã rõ. | Open
ISSUE-021 | P2 | Queue | Crawl worker mark running không CAS/optimistic lock | crawl_worker.py, crawl_queue.py | acks_late có thể double-run nếu claim không atomic. | UPDATE ... WHERE status='pending' RETURNING / version column. | Inject duplicate delivery → chỉ 1 execution side-effect. | Open
ISSUE-022 | P2 | RBAC | OrganizationMember.role không gate product APIs | models/organization.py, rbac.py | Schema có role nhưng API không dùng. | Hoặc enforce editor/viewer hoặc ẩn multi-member cho đến phase 2. | Viewer không write. | Open
ISSUE-023 | P2 | Deploy hygiene | Root *.html orphan trùng templates/ | seo_tool.html, keyword_*.html, rank_tracking.html ở repo root | Dễ sửa nhầm file không được serve. | Xóa hoặc archive; chỉ giữ templates/. | Deploy chỉ dùng Jinja templates. | Open
ISSUE-024 | P2 | Billing UX | Partial SePay payment marked processed (partial_paid) | sepay_webhook_service / payment activation | Underpay cần ops monitor thủ công. | Alert + admin UI backlog underpay. | Underpay không activate full plan. | Open
ISSUE-025 | P2 | Affiliate | Affiliate hook errors swallowed after payment | affiliate_payment_hooks.py | Commission có thể miss dù user đã paid. | Retry queue + dead-letter alert. | Simulate affiliate fail → retry tạo commission. | Open
ISSUE-026 | P2 | Test debt | test_content_ai_credit.py::test_charge_writes_ledger fail (MagicMock vs datetime) | saas_trial_service.py:83, tests/test_content_ai_credit.py | Mock trial expiry comparison TypeError. | Fix mock datetime hoặc guard isinstance trong service. | pytest test_content_ai_credit.py xanh. | Open | Observed FAIL

## Security & SaaS
Area | Control | Status | Severity | Finding | Related Issue IDs
Tenant isolation | Personal-org model (org_id≈user_id) | Partial | P0/P1 | user_id filters phổ biến; org resolver permissive; WP path strict | ISSUE-007,014
Tenant isolation | Cross-org write via client organization_id | Vulnerable (latent) | P0 | resolve_organization_id trusts client | ISSUE-007
Tenant isolation | Content AI / Publishing PG filters | OK | — | Tests isolation PASSED
Tenant isolation | Rank Tracking / Index / GBP / CSKH | User-only | P1 | Chưa org-ready | ISSUE-014
Auth | JWT + HttpOnly cookie + Bearer | OK | —
Auth | JWT lifetime 720h default | Weak | P1 | Stolen token window lớn | ISSUE-012
Auth | CSRF on cookie writes | OK (design) | P1 | Local CSRF tests failed do schema side-effect | ISSUE-019
Auth | Public unauth costly APIs | Vulnerable | P0 | schema / keyword-intelligence / serp-intel | ISSUE-006
RBAC | Admin vs user | OK | — | require_admin_user paths
RBAC | Org member roles | Not enforced | P2 | Schema only | ISSUE-022
Payments | SePay idempotency store | OK | — | Unique event + tx
Payments | SePay unsigned webhook mode | Vulnerable default | P0 | Require auth off | ISSUE-001
Payments | Always HTTP 200 on process errors | Ops risk | P1 | Need reconcile + alert | ISSUE-011
Credits | FOR UPDATE + ledger unique | OK | — | Strong against double debit
Credits | Reservation race IntegrityError | Edge fail | P1 | 500 instead of idempotent return | ISSUE-010
Credits | Unmetered Rank Tracking / GBP AI / SEO AI fix | Revenue leak | P0 |  | ISSUE-002,004,005
Prod flags | SAAS_ENFORCEMENT / CREDITS / COST_CONTROL | OK on prod env | — | All =1 in shared env.local
Prod flags | SEPAY_WEBHOOK_REQUIRE_AUTH | Missing/off | P0 | Not set → unsigned allowed | ISSUE-001
Prod flags | TENANT_CONTENT_AI_DUAL_READ | On (=1) | P1 | Cutover incomplete | ISSUE-013
Chatbot public | Widget CORS * + bot_id validation + rate limit | OK-ish | P2 | Ensure unguessable / domain allowlist
WP plugin | Pairing org strict + hashed codes | OK | —
Task poll | In-memory owner map | Broken multi-instance | P1 | IDOR/404 | ISSUE-008

## Performance
Area | Topic | Assessment | Severity | Detail | Related Issue IDs
Celery | acks_late + prefetch=1 | Good | P2 | Giảm mất job; cần claim atomic để tránh double work | ISSUE-021
Crawl | Distributed crawl job tenancy/lock | Weak | P1 | Thiếu tenant cols + running claim không CAS | ISSUE-009,021
Rank Tracking | JSON full-file RMW | Poor | P0 | O(n) IO + race mất data dưới concurrent users | ISSUE-003
Content AI bulk | SKIP LOCKED claim | Good | P1 | In-process scale limit; stale watchdog 900s/180s | ISSUE-017
Content AI write | LLM latency / timeouts | Watch | P2 | Reservation release on timeout paths cần regression
Index Control | ThreadPool workers=2 check-free | OK small | P2 | Multi-instance file/state pause races
Keyword async | Celery optional | Config dependent | P2 | Sync path có thể timeout request khi async off
Credits | Concurrent reserve same key | Edge 500 | P1 | IntegrityError unhandled | ISSUE-010
DB | credit_reservations migration | Risk | P1 | Missing table hard-fail runtime | ISSUE-019
Redis | Broker required for Celery features | OK | — | REDIS_URL set in prod
API public abuse | Unauth schema/SERP/intel | High risk | P0 | Cost amplification / DoS lên upstream APIs | ISSUE-006
GBP AI | Unmetered LLM under load | High cost risk | P0 | Nhiều user cùng lúc burn OpenAI budget | ISSUE-004
Chatbot public | Rate limit present | Mitigated | P2 | Monitor burst per IP/bot
Horizontal scale | In-memory registries (task owner, some JSON stores) | Not ready | P1 | Cần Redis/PG trước multi-instance | ISSUE-008,003

## Release Checklist
ID | Priority | Area | Action | Status | Related Issues | Acceptance test
REL-01 | P0 | Security | Bật SEPAY_WEBHOOK_REQUIRE_AUTH=1 + cấu hình API Key/HMAC SePay | Pending | ISSUE-001 | Forged unsigned webhook → 401
REL-02 | P0 | Billing | Gate + charge Rank Tracking check-now | Pending | ISSUE-002 | Hết credit → 402; đủ → debit
REL-03 | P0 | Data | Migrate Rank Tracking JSON → PG (hoặc file lock tạm) | Pending | ISSUE-003 | Concurrent create không mất row
REL-04 | P0 | Billing | Charge Google Map GBP AI actions | Pending | ISSUE-004 | Ledger entries per AI call
REL-05 | P0 | Billing | Bật SEO_SCORE_AI_FIX_BILLING_ENABLED hoặc ẩn AI Fix | Pending | ISSUE-005 | No free LLM burn
REL-06 | P0 | Security | Auth + credit cho schema-generator / keyword-intelligence / serp-intel | Pending | ISSUE-006 | Unauth → 401
REL-07 | P0 | Tenant | Membership-check trong tenant_org.resolve_organization_id | Pending | ISSUE-007 | Foreign org_id → 403
REL-08 | P1 | Queue | Persist async_task_registry trên Redis/DB | Pending | ISSUE-008 | Cross-worker poll OK
REL-09 | P1 | Tenant | Thêm user_id/org_id cho DistributedCrawlJob | Pending | ISSUE-009 | Cross-user job denied
REL-10 | P1 | Billing | Catch IntegrityError trong reserve_credits | Pending | ISSUE-010 | Concurrent same-key OK
REL-11 | P1 | Ops | SePay failed processing alert + reconcile cron verified | Pending | ISSUE-011 | Failed event repaired
REL-12 | P1 | Security | Giảm JWT_EXPIRE_HOURS prod (≤72) | Pending | ISSUE-012 | Expire enforced
REL-13 | P1 | Tenant | Tắt TENANT_CONTENT_AI_DUAL_READ sau cutover verify | Pending | ISSUE-013 | Flag=0
REL-14 | P1 | Billing | WP bulk SaaS entitlement/credit | Pending | ISSUE-015 | No plan → 403
REL-15 | P1 | Deploy | Chạy ensure_credit_saas_gate migration trên mọi môi trường | Pending | ISSUE-019 | App boot + pytest OK
REL-16 | P1 | Scale | Deploy dedicated Content AI bulk worker; document multi-instance | Pending | ISSUE-017 | No double job
REL-17 | P1 | Product | Gỡ/implement Keyword suggestion stub | Pending | ISSUE-016 | No stub UI
REL-18 | Must | Config | Xác nhận SAAS_ENFORCEMENT=1 CREDITS_ENABLED=1 COST_CONTROL_ENABLED=1 JWT_SECRET non-default | Done (flags=1) |  | Runtime guard
REL-19 | Must | Scope | Ship personal-workspace only; chưa announce shared organization | Pending decision | ISSUE-014,022 | Docs/pricing clear
REL-20 | Must | QA | E2E: register → trial → Content AI write → publish WP → checkout SePay → credit pack | Pending |  | Staging
REL-21 | Must | QA | E2E isolation: 2 users không thấy project/site/bot của nhau | Pending |  | Staging
REL-22 | Must | QA | Load smoke: 10 concurrent users Content AI + Keyword + analyze | Pending |  | No 5xx storm
REL-23 | Should | Ops | Bật payment reconciliation cron + alert SePay failed backlog | Pending | ISSUE-011,024
REL-24 | Should | Cleanup | Xóa orphan root HTML / dual chatbot prefix docs | Pending | ISSUE-018,023
REL-25 | Should | Tests | Fix failing tests (CSRF isolation env, content_ai_credit mock, runtime_guard asserts) | Pending | ISSUE-019,026 | CI green
REL-26 | Go/No-Go | Release decision | NO-GO official SaaS cho đến khi đóng hết P0 (REL-01..07) | NO-GO | P0 count=7 | Sau P0 → soft launch personal-only